## Bảng Module
Module | Tên Module | Mô tả chi tiết chức năng lõi
Module 1 | Lõi Nền tảng & Bảo mật | Xây dựng hệ thống xác thực người dùng, phân quyền, quản lý tài khoản và bảo mật JWT
Module 2 | Sản phẩm & Giỏ hàng | Quản lý sản phẩm, danh mục, giỏ hàng và tìm kiếm
Module 3 | Thanh toán & Đơn hàng | Xử lý checkout, tích hợp VNPay, quản lý đơn hàng
Module 4 | CMS & Báo cáo | Dashboard quản trị, thống kê doanh thu và xuất báo cáo

## Bảng công việc
STT | Module | Tên Công Việc | Mô Tả | Kỹ Năng Yêu Cầu | Ưu Tiên | Phụ Thuộc
1 | Module 1 | Thiet ke ERD Database | Thiet ke schema User, Role, Product, Order | SQL Server, Database Design | Cao | 0
2 |  | Setup Backend Project | Khoi tao ASP.NET Core Clean Architecture | C#, ASP.NET Core, Clean Architecture | Cao | 0
3 |  | API Dang ky | Validate input, hash password | C#, ASP.NET Core, BCrypt | Cao | 2
4 |  | API Dang nhap | Authenticate user, tra JWT token | C#, JWT, Authentication | Cao | 3
5 |  | Middleware Authorization | Xac thuc JWT va phan quyen API | C#, Middleware, JWT | Cao | 4
6 |  | API Quan ly User | CRUD user va role | C#, EF Core, ASP.NET | Cao | 5
7 |  | Redis Cache Session | Cache session login | Redis, C#, Caching | Vua | 5
8 |  | Upload Avatar | Upload anh len Cloudinary | C#, Cloudinary API | Vua | 6
9 |  | Setup Frontend | Init React + Vite + Tailwind | ReactJS, Vite, TailwindCSS | Cao | 0
10 |  | UI Auth | Form login/register | ReactJS, Axios, Validation | Cao | 9, 3
11 | Module 2 | Thiet ke DB Product | Schema Product, Category | SQL Server | Cao | 1
12 |  | API Product CRUD | CRUD san pham | C#, EF Core | Cao | 11
13 |  | API Search Product | Tim kiem va loc san pham | C#, LINQ, SQL | Vua | 11
14 |  | API Gio hang | Them, xoa, cap nhat cart | C#, Redis | Cao | 7, 11
15 |  | UI Product List | Hien thi danh sach san pham | ReactJS | Vua | 9, 12
16 |  | UI Product Detail | Trang chi tiet san pham | ReactJS | Vua | 12
17 |  | UI Cart | Giao dien gio hang | ReactJS, State Management | Cao | 14
18 | Module 3 | API Checkout | Tao don hang tu cart | C#, Business Logic | Cao | 14
19 |  | Tich hop VNPay | Thanh toan online | VNPay API, Encryption | Cao | 18
20 |  | Email Order | Gui email xac nhan | SMTP, MailKit | Vua | 18
21 |  | API Quan ly Order | Trang thai don hang | C#, EF Core | Cao | 18
22 |  | UI Checkout | Form dat hang | ReactJS, Axios | Cao | 17, 19
23 |  | Realtime Order | Trang thai realtime | SignalR | Thap | 21
24 | Module 4 | API Thong ke | Tong hop doanh thu | C#, SQL Aggregation | Cao | 21
25 |  | API Dashboard | Tong hop du lieu UI | C#, API Design | Cao | 24
26 |  | UI Dashboard | Chart doanh thu | ReactJS, Recharts | Cao | 25
27 |  | Role Permission UI | Quan ly role | ReactJS, RBAC | Vua | 6
28 |  | Export Excel | Xuat bao cao | EPPlus | Vua | 24
29 |  | Logging System | Ghi log he thong | Serilog | Thap | 2